## Risk Register
NovaPay — Risk Register
Reference: 09-Training-Awareness / Awareness-Plan.md — Information Security Risk Assessment
Legend: Yellow rows = example entries. Risk Score = Likelihood x Impact (auto-calculated). Likelihood/Impact rated 1 (low) to 5 (high). Overwrite or delete example rows before use.
Risk ID | Asset | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score (L x I) | Treatment Option | Control(s) | Owner | Status | Review Date
R-001 | User Accounts | Weak Passwords | Poor Hygiene | 4 | 4 | 16 | Reduce | A.5.17 | IT Ops | In Progress | 2026-09-01
R-002 | Servers | Missing Patches | Outdated OS | 5 | 4 | 20 | Reduce | A.8.9 | DevOps | Planned | 2026-08-15
R-003 | Cloud Provider | Outage | Supplier Dependency | 3 | 4 | 12 | Reduce | A.5.19 | Procurement | Planned | 2026-10-01
Summary
Total Risks Logged: | 3
High Risk (Score >= 15): | 2
Medium Risk (9-14): | 1
Low Risk (<=8): | 0
Open / In Progress: | 3